## Sheet1
Group Number - 8
Team Lead & Backend Lead- Vishnu R
Frontend Lead - Utkarsh Agarwal

## Sheet2
Project Status Check Report Team - 7
Sl no. | Employee ID | Name | Domain | Module | 2022-10-14 | 2022-10-15 | 2022-10-16 | 2022-10-17 | 2022-10-18 | 2022-10-19 | 2022-10-20 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-08
1 | 2526906 | Utkarsh Agarwal | Front end | Login | database defining,role assign and general entity and group division for certain parts | Entire front end login setup | sign up design | rework with database | create angular part of the code | Integration and error identification | presentation
2 | 2528260 | Yarmala Reddy | back end | Customer | database defining,role assign and general entity and group division for certain parts | entity,complaint id creation | complaint id mapping,database | rework rest api network | create angular part of the code | Integration and error identification | presentation
3 | 2526804 | vasuki | back end | user | database defining,role assign and general entity and group division for certain parts | service ,controller-manager | database creation and mapping | change front end | create angular part of the code | Integration and error identification | presentation
4 | 2530462 | umayal | back end | Engineer | database defining,role assign and general entity and group division for certain parts | entity,service,contoller-engineer | database creation | rework rest api network | create angular part of the code | Integration and error identification | presentation
5 | 2527463 | vishnu | backend | Admin | database defining,role assign and general entity and group division for certain parts | entity,service,contoller | database creation | rework rest api network | create angular part of the code | Integration and error identification | presentation
6 | 2528664 | Thota pavanchand | Front-End | Customer | database defining,role assign and general entity and group division for certain parts | dashboard
7 | 2525919 | vemu rejoice | Front-end | Admin | database defining,role assign and general entity and group division for certain parts | dashboard | signup&log in page | rest api network | create angular part of the code | Integration and error identification | presentation
8 | 2526832 | yellugari Reddy | Front end | user | database defining,role assign and general entity and group division for certain parts | dashboard | signup&log in page | change front end | create angular part of the code | Integration and error identification | presentation
9 | 2526625 | Vemula Sai | Front end | notes,tickets | database defining,role assign and general entity and group division for certain parts | dashboard | signup&log in page | rest api network | create angular part of the code | Integration and error identification | presentation
10

## Sheet3
Status Meeting Group - Name
Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collaboration
2020-10-14 | 9:30 | a | 2:30 | a | 6:20 | a
2020-10-15 | 9:30 | a | 1:00 | a | 6:20 | a
2020-10-16 | 9:30 | a | 2:00 | a | 6:10 | a
2020-10-17 | 9:30 | a | 3:00 | a | 6:30 | a
2020-10-18 | 9:30 | a | 1:30 | a | 6:10 | a
2020-10-19 | 9:30 | a | 1:30 | a | 5:30 | a
2020-10-20 | 9:30 | a